## Sheet1
Gant Chart for Year 3 Project
AI-Based Smart Bulb for Adaptive Home Automation
by Caleb Ram
| Semester 1 Weeks 1-12 | [10 empty] | Christmas Break
| September | October |  |  |  | November |  |  |  | December |  | December-January |  |  | January
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 1 | 2 | 3 | 12
Initial idea finialised (began 14th October) | bar: October 2 to October 4
Write up initial sections of Mid-Term Report including Literature Review and Introduction | bar: October 4 to October 5
Complete basic iOS application | bar: October 5 to November 7
Plan a simulator mode for iOS application | bar: November 8 to November 9
Add iOS application progress to Mid-Term Report | bar: November 9
Test iOS app on physical iPad and iPhone devices | bar: November 6 to November 8
Implement simulator mode for ESP32 bulbs | bar: November 9
Verify bluetooth mode in ESP32 smart bulb mode | bar: November 7
Update Mid-Term Report with bluetooth and simulator progress | bar: November 9
Component selection | bar: December 10
Component procurement | bar: December 11
Update Mid-Term Report with components chosen and arrived | bar: December 11
Submit first draft of Mid-Term Report to Supervisor | bar: December 11
Act on Supervisors feedback for Mid-Term Report | bar: December-January 1
Submit final Mid-Term Report before 2nd January 4pm | bar: December-January 2
Semester 2 Weeks 1-12
| January | October 2: Febraury; November 6: March; December 10: April; December-January 1: May
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Begin write-up of final report including Mid-Term report with updates if necessary
Build ESP32 Samrt Bulb | bar: Febraury 2
Implement ESP32 core features | bar: Febraury 2
Test core features, on/off, dimming and colour control | bar: Febraury 3
Update Final Report with core features | bar: Febraury 3
Begin PCB layout or veroboard design for compact housing | [13 empty] | Category | Estimated Costs | bar: Febraury 4
Plan and desgin 3D housing concept | [13 empty] | Hardware Components | 69 | bar: Febraury 4
Print first trial of 3D housing for ESP32 smart bulb | [13 empty] | Materials and fabrication | 23 | bar: Febraury 4
Update Final Report with 3D housing and PCB or veroboard designs | [13 empty] | Software and services | 0 | bar: Febraury 4
Start designing and adding more core hardware functions | [13 empty] | Contingency | 25 | bar: Febraury 5
Test additional features, AI dimming and colour control | bar: March 6
Update report with tests from extra features | bar: Febraury 4 to March 6
Conduct extended reliability testing and performance evaluation | bar: March 6 to March 7
Conduct security analysis and apply necessary measures | bar: March 6 to March 7
Update report regarding security and reliability testing | bar: March 6 to March 7
Begin designing and implementing a Web Application to run alongside on non-iOS devices | bar: Febraury 2 to Febraury 3
Test and implement all features from iOS app to Web Application | bar: Febraury 3 to Febraury 4
Update report with Web Application development | bar: Febraury 5 to March 6
Threading to increase run time of iOS app | bar: March 8
Prepare video tests to prove progress | bar: March 8 to April 10
Video: sign in process | bar: March 8
Video: forgot password sequence | bar: March 9
Video: connecting to ESP32 bulb and using test AI features | bar: April 10
Connect AI to Apple HealthKit test data | bar: Febraury 5 to March 6
Prepare presentation and rehearse | bar: April 10 to April 11
Update report with all progress and submit to supervisor in April | bar: March 9 to April 10
Submit final report before May 6th 4pm | bar: April 11